## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Resource
1 | Yes | Manually Scheduled | 4 Seasons Textile Website | 0 days | 0 | 0 |  | 1 | Sathish
2 | Yes | Manually Scheduled | Ecommerce Website | 30 days | April 1, 2022 8:00 AM | April 30, 2022 5:00 PM |  | 1 | Sathish
3 | Yes | Auto Scheduled | Requirements Gathering | 5 days | April 1, 2022 8:00 AM | April 5, 2022 5:00 PM |  | 2 | Dev Team
4 | Yes | Auto Scheduled | Functional Training | 5 days | April 1, 2022 8:00 AM | April 5, 2022 5:00 PM |  | 3 | Dev Team
5 | Yes | Auto Scheduled | Requirement Analysis | 5 days | April 1, 2022 8:00 AM | April 5, 2022 5:00 PM |  |  | Sathish
6 | Yes | Auto Scheduled | Design Development | 5 days | June 29, 2020 8:00 AM | July 3, 2020 5:00 PM | 3 | 3 | Sathish
7 | Yes | Auto Scheduled | Requirements Signoff | 1 days | April 5, 2022 5:00 PM | April 6, 2022 5:00 PM | 3,5 | 3 | John
8 | Yes | Auto Scheduled | Design Documentation | 1 days | April 5, 2022 5:00 PM | April 6, 2022 5:00 PM | 6 |  | Sathish
9 | Yes | Auto Scheduled | Design Signoff | 1 days | April 5, 2022 5:00 PM | April 6, 2022 5:00 PM | 8 |  | John
10 | Yes | Auto Scheduled | Development - Create a Login Page for the Customers | 10 days | April 2, 2022 5:00 PM | April 10, 2022 5:00 PM | 7, 9 | 3 | Shreyas
11 | Yes | Auto Scheduled | Development - Create a functionality to access the information from DB | 10 days | April 2, 2022 5:00 PM | April 10, 2022 5:00 PM | 7, 9 | 3 | Shreyas
12 | Yes | Auto Scheduled | Development - Create a Product page for Customers | 10 days | April 2, 2022 5:00 PM | April 10, 2022 5:00 PM | 7, 9 | 3 | Kenil
13 | Yes | Auto Scheduled | Development - Create a Shopping cart page | 10 days | April 2, 2022 5:00 PM | April 10, 2022 5:00 PM | 7, 9 | 3 | Kenil
14 | Yes | Auto Scheduled | Development - Create a authorization process for authenticating the payment | 10 days | April 2, 2022 5:00 PM | April 10, 2022 5:00 PM | 7, 9 | 3 | Nishil
15 | Yes | Auto Scheduled | Development - Create a Mobile Login Page for the Customers | 10 days | April 11, 2022 5:00 PM | April 20, 2022 5:00 PM | 7, 9 | 2 | Shreyas
16 | Yes | Auto Scheduled | Development - Create a Mobile functionality to access the information from DB | 10 days | April 11, 2022 5:00 PM | April 20, 2022 5:00 PM | 7, 9 | 3 | Shreyas
17 | Yes | Auto Scheduled | Development - Create a Mobile Product page for Customers | 10 days | April 11, 2022 5:00 PM | April 20, 2022 5:00 PM | 7, 9 | 3 | Kenil
18 | Yes | Auto Scheduled | Development - Create a Mobile Shopping cart page | 10 days | April 11, 2022 5:00 PM | April 20, 2022 5:00 PM | 7, 9 | 3 | Kenil
19 | Yes | Auto Scheduled | Development - Create a Mobile authorization process for authenticating the payment | 10 days | April 11, 2022 5:00 PM | April 20, 2022 5:00 PM | 7, 9 | 3 | Nishil
20 | Yes | Auto Scheduled | Unit Testing - Login Page Website/Mobile | 10 days | April 21, 2022 5:00 PM | April 28, 2022 5:00 PM | Task from 10 - 19 | 3 | Shreyas
21 | Yes | Auto Scheduled | Unit Testing - functionality to access the information from DB | 10 days | April 21, 2022 5:00 PM | April 28, 2022 5:00 PM | Task from 10 - 19 | 3 | Shreyas
22 | Yes | Auto Scheduled | Unit Testing - Product page for Customers | 10 days | April 21, 2022 5:00 PM | April 28, 2022 5:00 PM | Task from 10 - 19 | 3 | Kenil
23 | Yes | Auto Scheduled | Unit Testing - Shopping cart page | 10 days | April 21, 2022 5:00 PM | April 28, 2022 5:00 PM | Task from 10 - 19 | 3 | Kenil
24 | Yes | Auto Scheduled | Unit Testing - Authorization process for authenticating the payment | 10 days | April 21, 2022 5:00 PM | April 28, 2022 5:00 PM | Task from 20 - 24 | 3 | Nishil
25 | Yes | Auto Scheduled | QA Testing - Login Page Website/Mobile | 10 days | April 21, 2022 5:00 PM | April 28, 2022 5:00 PM | Task from 20 - 24 | 3 | QA Team
26 | Yes | Auto Scheduled | QA Testing - functionality to access the information from DB | 10 days | April 21, 2022 5:00 PM | April 28, 2022 5:00 PM | Task from 20 - 24 | 3 | QA Team
27 | Yes | Auto Scheduled | QA Testing - Product page for Customers | 10 days | April 21, 2022 5:00 PM | April 28, 2022 5:00 PM | Task from 20 - 24 | 2 | QA Team
28 | Yes | Auto Scheduled | QA Testing - Shopping cart page | 10 days | April 21, 2022 5:00 PM | April 28, 2022 5:00 PM | Task from 20 - 24 | 3 | QA Team
29 | Yes | Auto Scheduled | QA Testing - Authorization process for authenticating the payment | 10 days | April 21, 2022 5:00 PM | April 28, 2022 5:00 PM | Task from 20 - 24 | 4 | QA Team
30 | Yes | Auto Scheduled | Deployment- Login Page Website/Mobile | 10 days | March 9, 2022 8:00 AM | May 24, 2022 5:00 PM | Task from 25 - 29 | 4 | Deployment Team
31 | Yes | Auto Scheduled | Deployment - functionality to access the information from DB | 10 days | May 25, 2022 8:00 AM | June 28, 2022 5:00 PM | Task from 25 - 29 | 4 | Deployment Team
32 | Yes | Auto Scheduled | Deployment - Product page for Customers | 10 days | June 29, 2022 8:00 AM | July 26, 2022 5:00 PM | Task from 25 - 29 | 4 | Deployment Team
33 | Yes | Auto Scheduled | Deployment - Shopping cart page | 10 days | March 2, 2022 8:00 AM | April 26, 2022 5:00 PM | Task from 25 - 29 | 3 | Deployment Team
34 | Yes | Auto Scheduled | Deployment - Authorization process for authenticating the payment | 10 days | March 2, 2022 8:00 AM | April 26, 2022 5:00 PM | Task from 25 - 29 | 4 | Deployment Team

## Resource_Table
ID | Name | Type | Email Address | Hours Needed | Standard Rate/Units Required | Budget Provided
1 | Team | Work |  |  | $0.00/h | 5,93,000- Required for the techical team
2 | Resources- Developer/Testers | Work |  | 288 | $40.00/h | 100000
3 | Team Lead | Work |  | 288 | $55.50/h | 5000
4 | Business Analysts | Work |  | 288 | $45.00/h | 3000
5 | Scrum Master | Work |  | 288 | $50.00/h | 5000
6 | Project Manager | Work |  | 288 | $80.00/h | 10000
7 | Operational Manager | Work |  | 288 | $80.00/h | 20000
8 | Delivery Manager | Work |  | 288 | $100.00/h | 30000
9 | Procurement Manager | Work |  | 288 | $85.00/h | 30000
10 | Risk Manager | Work |  | 288 | $80.00/h | 30000
11 | Communication Manager | Work |  | 288 | $80.00/h | 30000
12 | Ethics and Privacy | Work |  | 288 | $80.00/h | 30000
13 | Audit Incharge | Work |  | 288 | $60.50/h | 30000
14 | Project Coordinator | Work |  | 288 | $70.00/h | 30000
15 | Architect | Work |  | 288 | $80.00/h | 30000
16 | Design Engineer | Work |  | 288 | $65.00/h | 30000
17 | Human Resource Manager | Work |  | 288 | $70.50/h | 30000
18 | Financial Accountant | Work |  | 288 | $60.00/h | 30000
19 | Quality Manager | Work |  | 288 | $80.00/h | 30000
20 | Quality Check Manager | Work |  | 288 | $80.00/h | 30000
21 | IT Support | Work |  | 288 | $40.00/h | 30000
22 | IT Team Lead | Work |  | 288 | $60.50/h | 30000
28 | Materials | Material |  | NA | 2000 Units | 100000
29 | Servers | Material |  | NA | 10 Units | 100000
30 | DataBase | Material |  | NA | 5 units | 100000
31 | Wiring/Cabling | Material |  | NA | 10 Units | 1000
32 | Servers Cooling system | Material |  | NA | 3 Units | 5000
33 | Hosting Services | Material |  | NA | 1 Units | 5000
34 | Analytics Tools | Material |  | NA | 5 Units | 5000
35 | Subscriptions | Material |  | NA | 1 Units | 50000
36 | Marketing | Material |  | NA | 1 Units | 5000
37 | Warehouse Rent | Material |  | NA | 1 Units | 5000
38 | Office Space Rent | Material |  | NA | 1 Units | 5000
39 | Warehouse Maintainance Tools | Material |  | NA | 100 Units | 5000
40 | House Keeping | Material |  | NA | 5 Untis | 10000
41 | Miscellaneous | Material |  | NA | NA | 10000
Note
The above Budgeting is variable and can be changed over time, it is just an approximation of the project |  |  |  |  | Total | 999000
NA - | Not Assigned